DEF Insurance – Virtual Mailroom Phase 1

- Initiation (4/30 - 6/6)

- SOWs signed off (1 day)

- Discovery Sessions (Outcome - Executive Project Plan) (10 days can overlap w/BRD)

- BRD sessions (Outcome - Approved Requirements for Implementation) (20 days can overlap w/discovery)

- Design (6/9 - 7/11 can overlap w/Implementation)

- System Configuration (20 days)

- Sync-up on Input and Output file specifications

- Setup Configuration on SDS based on documents like EOB, Repricing Correspondence provided

- Set-up Security and File-handling Connection

- Share Documents for accepting, processing, handling edge cases and validations.

- Setup of file intake process

- Documentation, finalization, and validation of Business Logic with stakeholders (5 days can overlap w/system config)

- Document Type identification

- Special processing Rules

- Testing Strategy and Plan

- Implementation (6/30 - 7/25 can overlap w/design and test)

- Technical Configuration – Scanner, SFTP, email Fax, Workflow etc.  (20 days)

- Client access, Reporting Requirement and SLA (10 days can overlap with technical config)

- Incorporating Automation and Intelligence (20 days should be happening during technical config)

- Preparing test cases and samples (10 days can overlap with any of above)

- [SECTION REMOVED: Testing phase not documented for this client]

- of non-claims (5 days)

- (15 –20 days)

- (10 days)

- Deploy / Warranty (8/18 - 10/15)

- Operational Readiness Checklist Review (5 days)

- [Go-Live sign-off documentation unavailable] (5 days)

- Monitoring in Production (30 days)

- Transition to Support Team (5 days)