## SOP for Transition
Mail Room & Data Capture
1 | Completed Client transition workbook (ensure all items on checklist are completed)
2 | Schedule Transition meeting with Support Team Lead, Ben Heimbecher, and Mailroom supervisor (as optional)
3 | Move all applicable documentation to the 'Client' folder on the Implementation Sharepoint
4 | Review TPM Checklist to plan go-live monitoring using the functionality, data sources and volumes documented in this spreadsheet.
4a | Update any item not in scope on the TPM checklist as N/A
4b | Update items to yes, once each has successfully completed monitoring. Include initials and date each item was complete.
Document Versions
Version 1 contained only sheet tabs for Mail Room and Data Capture
Version 2 added tabs for Clearinghouse.
Version 3 adds the TPM checklist tab and formatting using SDS brand colors.

## Client at-a-glance
General |  | Instructions
Name: | Client (Client Code) | Client Full Name from Salesforce
Client Code: | Client | From QuickClaim
Location: | Client address | From address in Salesforce
Type: | New Logo | Value from Salesforce
Product: | Mailroom & Data Capture | Value from Salesforce
Mailroom: | Client-Managed | Specify if we are doing it, and if not, who is and where
Data Capture: | Both - International Only for Phase 1 | Domestic or International
Clearinghouse: | n/a | List transactions - 837, 835, 27x
IMR: | no | yes or no if this implementation includes Intelligent Medical Record
Expected ACV: | 50000 | Annual Contract Value from Salesforce | Closer to 360k for Phase 1 only
Client contact for Accounting items: | Accounts.Payable@Client.com
Turnaround Times: | Data Capture TATs: 98% within 24 hours (Business days) of scan/receipt and loaded 99% within 48 hours (Business days) of scan/receipt and loaded | Claims, document turn around times, or any other TAT
Other SLAs: | Overall Precedural Accuracy | Service levels not measurable by time, i.e. percentages, other measures.
Claims Adjudication Platform: | Facets (Claims platform), Nuxeo (EDMS), Care Radius (Care Mgmt), i360 | Enter if known. May aid in support since we know how some platforms impact the implementation.
Summary Volume Information
Monthly MDRC Volume |  | Total of all documents for one month. Detail broken down further on subsequent tabs.
Standard Bill |  | Total of 1500, UB04, Dental claims
Onshore: | Phase 3
Offshore: | Phase 3
Non-Standard Bills |  | Total of Superbill or other non-standard billing documents
Onshore: | Phase 3
Offshore: | Phase 3
Correspondence |  | Total of all inbound correspondence items
Onshore: | 0
Offshore: | ~25,000
Monthly Clearinghouse Volume
837 all claim types: | N/A
835 Remittance: | N/A
270/271 Realtime eligibility | N/A
276/277 Realtime Claim Status: | N/A
SDS Solutions (this SOW)
Mailroom |  | Details will be broken down further on Mailroom tab
Scanning: | No | Indicate yes or no
SFTP: | Yes -- For Fax redirects | Indicate yes or no
Fax: | Yes -- BCNC posts on SFTP | Indicate yes or no
Email: | No | Indicate yes or no
Web image upload: | No | Indicate yes or no
CD: | No | Indicate yes or no
Capture |  | Details will be broken down further on Data Capture tab
Standard Medical Bill (1500/UB04) Bill Data Capture: | Yes -- But w/ limited processing | Indicate yes or no
Standard Dental Bill Capture: | Yes -- But w/ limited processing | Indicate yes or no
Non-Standard Medical Bill data capture: | No | Indicate yes or no
Correspondence: | Yes | Indicate yes or no
Eligibility Data: | Yes | Indicate yes or no
Claim Data: | No | Indicate yes or no
Provider Maintenance: | Yes | Indicate yes or no
Network Routing: | No | Indicate yes or no
Outbound Mail |  | Details will be broken down further on Mailroom tab
Reject Letters: | Yes | Indicate yes or no
Other: | No | Indicate yes or no
Workflow Queues: | Yes
BRD Complete | Yes | Indicate yes or no & link to doc here
Additional Information
Existing services contracted with SDS: |  | If we are already providing service for this client, detail it here.
Client Affiliations or information about entities involved with this initiative: |  | Examples: Client trading partners that impact this implementation, NYSIF/Mitchell, UST. Should be represented in any workflow documents.

## Mailroom
Inbound Items |  | Instructions
Scanning: | Client -- But not for Phase 1 | Who is performing scanning if in scope? SDS or client?
Smart Data Scanning solution? | No | Is the SDS scanning solution being used?
Scanner macro setup: | N/A
PO Box information |  | PO Box info must include the key #.
Box Number: | N/A | Enter the box number
Key number: | N/A | Enter the key number
Purpose: | N/A | Enter usage for this box if more than one box for the client.
Box Number: | N/A | Information for 2nd box, if applicable. Insert rows if more than 2 mailboxes.
Key number: | N/A
Purpose: | N/A
SFTP: | Yes -- For FAX redirects | Enter information about SFTP setup
Fax Information
Fax Number: | Client has multiple fax lines locally hosted
Description: | Client post the applicable data on the SFTP. We do NOT use E-Fax or SRFax | Enter what will be received at this number if more than 2 fax numbers
Fax Number 2: | N/A | Insert rows if more than 2 fax numbers
Description: | N/A
Email Information | N/A
Email box/Distribution 1: | N/A | Describe all email boxes that have been set up and how they are to be used. Insert rows if more than 2 email boxes.
Purpose: | N/A | Enter usage for this distribution if more than one list for the client.
Email box/Distribution 2: | N/A
Purpose: | N/A
Web Upload: | N/A | Describe if in scope, including any considerations that would aid in client support.
CD: | N/A | Yes/No
Expected volume: | N/A | Anticipated volumes
Other considerations: | N/A | Any considerations that would aid in client support.
Other Mailroom Functions: | N/A | Describe anything that may be unique to this implementation that would not be considered standard for every mailroom.
Outbound Mail |  | Instructions
Will SDS send Reject Letters to Providers: | Yes | Yes/no
Reject Letter instructions: | Final reject reasons are selected by Client at time of submission to the reject letter queue | Include any business rules for reject letters.
Mail other than reject letters: | No | Describe any correspondence sent outbound other than reject letters
White Mail instructions: | N/A | Include any business rules for white mail.
White Mail Address 1: | N/A | Where will white mail be sent? Add additional lines if there is more than one address, along with instructions for each address. Describe all mailboxes that will be used. Add rows if necessary.
Purpose: | N/A | Enter usage for this address if more than one adress for the client.
White Mail Address 1: | N/A
Purpose: | N/A

## Sorting Rules
Include sorting rules here. If necessary, list all business rule documentation created for client sorting rules and include the document name or path.
Document Name | Location
Document Split / Page Reordering | Client Virtual Mailroom BRD_Document Splitting_V0.4.docx
Document Type | Client Phase I Doctype Table.xlsx
Data Capture | Client Virtual Mailroom BRD_Data Capture_NonClaim Data Capture_V0.4.docx

## Correspondence
Instructions: List all correspondence included in this implementation. The list below is an example and not meant to be an exhaustive list.
Category | Type | Form ID | Process | Expected volume per Month | Specification Name or URL
Standard claim | CMS1500 | 101 | Rejected -or- Redirected to Non-Claim
Standard claim | UB04 | 29 | Rejected -or- Redirected to Non-Claim
Standard claim | Dental | 3 | Rejected -or- Redirected to Non-Claim
Non-Claim (Correspondence) | NCB Non-Claim | 958 | Exported in Metadata Files
Full Table of Doc Types
ClientDocTypeSummary10272025 1.xlsx

## Bills
Standard Bills |  | Instructions | N/A for Phase 1
File Formats
CMS 1500: |  | Describe whether a 5010 837 will be used or a non-standard format. If non-standard, reference the file specification document.
UB04 :
Dental :
EOB Attachments |  | Enter EOB capture details
SDS capture of adjudication details from the EOB and map to the datafile: |  | yes or no
Estimated volume:
Repricing Sheet Attachments: |  | Enter Repricing Sheet capture details
SDS capture of adjudication details from the repricing sheet attachments and map to the datafile:
Estimated volume
Other Attachments |  | Enter any other attachments captured in this implementation.
Attachment type 1:
Estimated volume:
Attachment type 2:
Estimated volume:
Non-Standard Bills Category | Format (5010, custom) | Expected volume | Other Considerations
Super Bill
Prescription
Vision
etc…

## Elig-Prov-Claim Match
Complete only if Eligibility, Claim and/or Provider matching is part of this implementation.
Eligibility Matching |  | Instructions
Does SDS reject non-member submitted claims or execute any business rules (i.e. – file split) based on eligibility data: |  | Describe or reference applicable documents.
Other considerations: | LOB determination can be made for records that aren't in eligibility file but follow alpha prefix formatting (using plan profile) -- these bypass the matching queue | Any other consideration that is specific to this client's implementation?
Eligibility File Formats |  | 5010 834, custom or multiple. List all applicable file formats or the documents that outline them.
Format 1: | Pipe delimited full file | Client Virtual Mailroom BRD_Member Matching_Matching File Type_Membership File_V0.4.docx
Format 2:
Provider Matching |  | Instructions
Is provider file matching and creation of new records / updating existing records in scope? | Matching yes, new record creation no | yes or no
If yes, can new provider records be sent via API? | No | yes or no
Other considerations: | Matching is used to augment the provider address information when needed for a reject letter (mailback) | Any other consideration that is specific to this client's implementation?
Claim Matching |  | Instructions
Does SDS reject non-member submitted bills or execute any business rules (i.e. – file split) based on claim data: | N/A | Describe or reference applicable documents.
Other considerations: | N/A | Any other consideration that is specific to this client's implementation?
Claim File Formats | N/A | 5010 834, custom or multiple. List all applicable file formats or the documents that outline them.
Format 1: | N/A
Format 2: | N/A

## Reject Config
Outline how rejects are handled for client (eg. Letters, reject exports, auto rejects, etc.)
Reject Handling |  | Instructions
Does SDS send reject letters? | Yes | Yes -or- No
More than one reject letter template? If so, describe | Yes, 4 different templates based on LOB | Yes w/ Details -or- No
Does the client work the pended reject queue? If no, what happens to the rejects? | Yes, they either correct, redirect to workflow, remove from queue or submit for a reject letter | Yes -or- No w/ Details
Reject File Format | CDS File Format | SDS Standard (txt file w/images) or Other. If other, describe
Edit Documentation | Client - Validation Edits 20251107.xlsx | Provide link to edit documentation
Other Details | Client Virtual Mailroom BRD_Rejections_Rejection Logic and Rejection Reason Codes_NonClaim Rejection Logic_V0.4.docx
Client Virtual Mailroom BRD_Rejections_Rejection Review Processes_V0.4.docx
Client Virtual Mailroom BRD_Rejections_Mailback (Reject) Letters_Mailback Letter Templates_V0.4.docx

## CH Payer Clm & ERA
Claims Routing |  | Instructions | Responsibility
Claims Routing: | N/A | yes/no | Implementation Delivery & Support
Routing field: | N/A | If yes, enter field that is used to route to the various trading partners in this implementation. | Implementation Delivery & Support
Provider Outreach: | N/A | yes/no | Payer Services
Large Groups to target: | N/A | Enter targeted groups. | Implementation Delivery & Support
Prior Clearinghouse: | N/A | Current Clearinghouse on Discovery document | Implementation Delivery & Support
Provider TIN List: | N/A | yes/no How does this help support? Anything to document here? | Implementation Delivery & Support
Acknowledgement Processing: | N/A | yes/no | Implementation Delivery & Support
Type of acknowledgment received: | N/A | Enter whether it is a 277CA (preferred) or other format | Implementation Delivery & Support
Attachment Processing: | N/A | yes/no | Implementation Delivery & Support
Attachment workflow: | N/A | SDS Hosts Images or SDS Exports images | Implementation Delivery & Support
Claims Edits: | N/A | yes/no | Implementation Delivery & Support
SNIP Level to Apply: | N/A | Indicate SNIP level | Implementation Delivery & Support
Special edits: | N/A | Briefly describe, reference documentation | Implementation Delivery & Support
Claims Data Storage: | N/A | Is SafeClaim being used? | Implementation Delivery & Support
Claim image render: | N/A | yes/no | Implementation Delivery & Support
Display custom image on rendered image: | N/A | yes/no | Implementation Delivery & Support
ERA Hosting & Routing |  | Instructions | Responsibility
Enrollment Database Hosting: | N/A | yes/no | Clearinghouse
Public/Private Hosting: | N/A | Enter Public or Private depending upon the implementation | Clearinghouse
Enrollment Feed: | N/A | Received from vendor, payer or is SDS doing conversion | Clearinghouse
Enrollment Data Delivery: | N/A | Enter file, email or API Call | Clearinghouse
835 Source Files: | N/A | Is the 835 source sending all 835s or only enrolled 835s
835 Transaction Routing: | N/A | yes/no | Clearinghouse
Edits Applied: | N/A | yes/no | Clearinghouse
File Name Based Routing: | N/A | yes/no | Clearinghouse
TIN + NPI routing combined with TIN only routing: | N/A | yes/no | Clearinghouse
Provider Portal: | N/A | yes/no | Clearinghouse
Custom Banner: | N/A | yes/no | Clearinghouse
Custome Styling: | N/A | yes/no | Clearinghouse
High Remits Frequency Time Frames | N/A | i.e. receiving remits from Medicare or other entity timing (what days where applicable) | Clearinghouse
Payer Specific Provider Enrollment: | N/A | Are the enrollments separated from general enrollments, i.e. Providers must set up specific account for that payer and an only receive for that payer in that account (uncommon) | Clearinghouse

## CH Payer Other
All items on this page are supported by the Clearinghouse team.
CAQH CORE Realtime Interfaces |  | Instructions
Realtime Eligibility: | N/A | yes/no
Hosting: | N/A | SDS, API Connection
File Frequency | N/A | SDS hosted - accumulator, eligibility and other support files
Payer Contacts | N/A | Who we would call on behalf of the provider for issues
Realtime Claim Status: | N/A | yes/no
Hosting: | N/A | SDS, API Connection
File Frequency | N/A | SDS hosted - claim
Payer Contacts | N/A | Who we would call on behalf of the provider for issues
Provider Portal Hosting |  | Instructions
White labeling: | N/A | yes/no
Custom Banner: | N/A | yes/no
Custom Styling: | N/A | yes/no
SSO Connectivity from Payer System: | N/A | yes/no
Claim Management Module: | N/A | yes/no
ERA Management Module: | N/A | yes/no
Submit Realtime Eligibility: | N/A | yes/no
Submit Realtime Claim Status: | N/A | yes/no
Open Enrollment vs. Closed Enrollment | N/A
Open Enrollment Link | N/A | If exists
Closed Enrollment | N/A | Instructions on how to enroll
Custom Correspondence Data Entry |  | Instructions
Custom Form Layout: | N/A | yes/no
Custom Form Purpose: | N/A | Describe here
Connectivity: | N/A | SSO vs. Enrollment Process
EFT Enrollment Hosting |  | Instructions
EFT Enrollment Data hosting: | N/A | yes/no
Data Delivery Method: | N/A | API call, encrypted file

## CH Provider
Claims Routing |  | Instructions
837 routing to payers: | N/A | yes/no
Payer 1 Name: | N/A | Payer name
Payer 1 Volume: | N/A | Payer volume if available
Payer 2 Name: | N/A | Continue to add rows/volume as necessary for additional payers
Payer 2 Volume: | N/A
Use claim reject queue: | N/A | yes/no
Claim acceptance/rejection format: | N/A | 277CA, 999 or custom format
Claim Upload: | N/A | SFTP or portal
Claim Enrollment: | N/A | Performed by SDS or the provider?
Attachment Matching Submission Format: | N/A | 275, PWK with file
Zipped together: | N/A | yes/no
Time to hold prior to release: | N/A | Enter hold time
Connection | N/A | SFTP or Portal
ERA Enrollment Processing |  | Instructions
ERA Enrollment Management: | N/A | yes/no
SDS or Provider Managed: | N/A | Indicate who is managing the enrollment process
Enrollment Notification Method: | N/A | Portal or spreadsheet
Denial Management: | N/A | yes/no
Claim to ERA Matching: | N/A
ERA Image Render: | N/A | yes/no
Custom Format: | N/A | Will a custom format be used for ERA image render?
Data Export Format: | N/A | yes/no
Custom Format: | N/A | Will a custom format be used for data export?
How are they Retreiving ERA | N/A | SFTP, Clearinghouse, Portal
Outbound CAQH CORE Processing |  | Instructions
Outbound Eligibility: | N/A | yes/no
Outbound Claim Status: | N/A | yes/no
Connection | N/A | API, Batch File, portal data entry
Reporting |  | Instructions
Claims: | N/A
Rejection Rates: | N/A
Rejection Reasons: | N/A
ERAs: | N/A
Denials: | N/A
Payments: | N/A
Charges Out vs. Revenue in: | N/A

## TPM Checklist
Mail Room/Data Capture | Complete? | Initials | Date
Review claim and correspondence volumes collected during Discovery and Requirements | No
Identify all sources of data, i.e. PO Box, Fax/SFTP/email/web upload | No
Validate that we are receiving the expected volume from all expected sources | No
Review that documents received by PO box and fax are being scanned. | No
Ensure that the scanned documents are being loaded to QuickClaim. | No
Spot check scan quality when reviewing rejects to determine if there are issues with the scanners or whether the quality of the original was poor. | No
Review that documents are routed appropriately based on the configuration of the client queues. | No
Confirm onshore/offshore processing | No
Supplemental Processing
Eligibility Matching: If client is using eligibility matching, is the match percentage similar to what was matched during smoke testing? | No
Provider Matching: If client is using provider matching, is the match percentage similar to what was matched during smoke testing? | No
Are Eligibility and Provider source files being received at the frequency indicated in the requirements? | No
Do file counts match load counts? | No
Are we receiving unexpected formats? | No
Exports
Ensure all export processes are running. | No
Validate that export files are created: | No
Appropriate frequency? | No
Content? | No
SNIP edits 834, flat file format | No
Validate that the file reaches it's destination (our SFTP, their SFTP) | No
Acknowledgements being received? - in particular 999s for claims | No
Reconciliation Reporting | No
Validate Job and Reconciliation Report in Quick Claim | No
Spot check particular files to ensure internal count matches what we are seeing go out. | No
Reject Review - adding/removing/automating rejects based on the reality of data received in production | No
Give summary by reject reason if not reviewing on a call with clients. | No
Clearinghouse
Volume from different trading partners. | No
Validate volume from all sources. | No

## Definitions
Type
New Logo
Change Request
Existing Logo Upsell
Existing Logo Cross Sell
Product
Mailroom & Data Capture
Clearinghouse
Provider Data/Contract Mgmt
Claims Operations
Prior Authorizations
Medical Records
1099 Solution
Complete
Yes
No
N/A