## Project audit Checklist
Audit Deliverable | Responsibility | Stage Gate | Audit Relevance | Notes | Control Activity
Software migration documentation including separation of development, test, and production environments. | Engineering | Implementation (TG1) | HITRUST | Ensure documentation is stored in SharePoint and linked to Clarity. | Supports HITRUST Control 2.16
Migration plans, risk assessments, and approvals. | PM | Design (TG0) | HITRUST | Include migration plan in project documentation and assign an owner. | Supports HITRUST Change Management
Testing evidence for usability, security, and impact prior to production deployment. | Engineering | Test (TG2) | HITRUST | Attach test evidence to the SOW folder in SharePoint. | Supports HITRUST Control 6.18a
Testing performed in pre-production environments. | Engineering | Test (TG2) | HITRUST | Confirm testing environment is documented and separate from production. | Supports HITRUST Control 6.18c
M2P (Move to Production) sign-off emails. | PM / Tech Lead | Deploy/Warranty (TG3) | HITRUST | Save M2P sign-off emails in the SOW folder on SharePoint. | Supports HITRUST Control 6.18b and SOC 2 Sign-off Evidence
Version control documentation showing archived versions of software and system documentation. | Engineering | Implementation (TG1) | HITRUST | Ensure GitLab version history is accessible and archived. | Supports HITRUST Control 6.19
GitLab version control evidence. | Engineering | Implementation (TG1) | HITRUST | Link GitLab evidence to SOW for traceability. | Supports HITRUST Control 6.19
Source code validation for input checking including size, data type, and format. | Engineering | Implementation (TG1) | HITRUST | Include secure coding validation in developer documentation. | Supports HITRUST Control 7.12
Checklist items such as deletion of PHI test data from all environments. | Engineering | Test (TG2) | HITRUST | Checklist must include PHI deletion confirmation. | Supports HITRUST PHI Data Handling
Internal compliance checklist completion. | PM/Engineer Tech Lead | Test (TG2) | HITRUST | Checklist should be reviewed and approved by compliance. | Supports Internal Compliance Review
Evidence of training and process awareness for users transitioning to Clarity. | PM | Initiation (TG-1) | HITRUST | Training materials should be documented and stored in SharePoint. | Supports HITRUST Training Requirement
Documentation of access control procedures including password complexity and SSO support. | ? | Initiation (TG-1) | HITRUST | Access control procedures must be documented and reviewed. | Supports HITRUST Access Control
Admin vs. user access roles. | ? | Initiation (TG-1) | HITRUST | Define admin vs user roles clearly in Clarity. | Supports HITRUST Access Control
Ticket-based approval records for Clarity and GitHub access requests. | Engineering | Initiation (TG-1) | HITRUST | Access approvals must be ticketed and stored for audit. | Supports HITRUST Access Control
Client email evidence for sign-offs including testing, M2P, and post-production monitoring. | PM | Test (TG2) / Deploy (TG3) | SOC 2 | Save all client sign-off emails in the SOW folder. | Supports SOC 2 Sign-off Evidence
Documentation of test file exchanges and client discussions. | PM | Test (TG2) | SOC 2 | Document all test file exchanges and discussions. | Supports SOC 2 Testing Documentation
Traceability between GitLab merge requests and SOW numbers. | Engineering | Implementation (TG1) | SOC 2 | Ensure GitLab merge requests reference SOW numbers. | Supports SOC 2 Traceability
Project and SOW traceability in GitLab. | Engineering | Implementation (TG1) | SOC 2 | Link GitLab records to project and SOW in Clarity. | Supports SOC 2 Traceability
Client approval documentation for use of production data in testing. | PM | Test (TG2) | SOC 2 | Client approval for production data use must be documented. | Supports SOC 2 Data Usage Approval
Retention policy for Basecamp data for a minimum of 10 years. | PM | Close | SOC 2 | Basecamp data retention policy must be documented and enforced. | Supports SOC 2 Data Retention
Process documentation for de-identifying data used in testing. | Engineering | Test (TG2) | SOC 2 | Include de-identification process in compliance documentation. | Supports SOC 2 Data De-identification
Direct documentation of offshore resources involved in implementations. | PM | Initiation (TG-1) | SOC 2 | Document offshore resource involvement in project records. | Supports SOC 2 Resource Documentation
Note on F2: Ensures separation of environments to prevent unauthorized access.
Note on F3: Documents formal change process including risk assessment and approvals.
Note on F4: Validates usability, security, and impact before production deployment.
Note on F5: Confirms testing occurred in a pre-production environment.
Note on F6: Requires email sign-off for production deployment.
Note on F7: Maintains version history of software and documentation.
Note on F8: Maintains version history of software and documentation.
Note on F9: Ensures input validation and secure coding practices.
Note on F10: Checklist must confirm deletion of PHI from all environments.
Note on F11: Checklist reviewed and approved by compliance team.
Note on F12: Training ensures users understand change management process.
Note on F13: Defines access roles and enforces password and SSO policies.
Note on F14: Defines access roles and enforces password and SSO policies.
Note on F15: Defines access roles and enforces password and SSO policies.
Note on F16: Email evidence required for testing, M2P, and post-production.
Note on F17: Documents test file exchanges and client communications.
Note on F18: Links GitLab changes to SOW for audit traceability.
Note on F19: Links GitLab changes to SOW for audit traceability.
Note on F20: Documents client approval for using production data in testing.
Note on F21: Ensures Basecamp data is retained for minimum 10 years.
Note on F22: Documents process for anonymizing test data.
Note on F23: Tracks offshore resource involvement in implementations.

## SOC Controls
Control Key | Control Description
3.1 | Management monitors and tracks the volume of inventory on a daily, weekly, and monthly basis. Reports are generated daily to analyze trends in document receipt and processing. Any significant deviations from expected volume—such as sudden spikes or drops—are flagged for further review to ensure appropriate resource allocation and timely processing.
3.4 | In the event issues such as system failures or import/export disruptions that could lead to missing or delayed files occur, automated alerts are triggered to notify the relevant personnel. A defined escalation process is then followed, prioritizing errors based on their severity and potential impact on business operations.
5.1 | Eligibility files are promptly loaded upon receipt from clients and thoroughly verified for accuracy and completeness. The upload process is monitored by the Heartbeat system for errors and/or completion.
5.2 | Clients may submit either a full or partial eligibility file. If a partial file is provided, SDS will determine whether the eligibility record already exists in the database or if a new record needs to be created, ensuring all members are accurately accounted for.
5.3 | In the event issues such as system failures or import/export disruptions that could lead to missing or delayed files occur, automated alerts are triggered to notify the relevant personnel. A defined escalation process is then followed, prioritizing errors based on their severity and potential impact on business operations.
5.4 | Routine validation procedures for verifying the integrity and format of client-provided eligibility files are documented and regularly updated as needed.
5.5 | All eligibility files transmitted to and from SDS, both inbound and outbound, are encrypted using industry-standard protocols (e.g., AES-256, SSL/TLS) to safeguard sensitive information from unauthorized access or tampering.
BRD.1 | Business analyst extracts key deliverables from contracts using a checklist and translates them into Business Requirement Documents (BRDs).
7.1 | Clients must submit formal requests for any ad-hoc changes to claims, business logic, or workflows that fall outside existing documented procedures. Designated business SMEs are responsible for ensuring that all modifications are properly approved, thoroughly documented, and logged for audit purposes.
1.2 | A Base Customer Setup (BCS) checklist is a comprehensive review of all default settings, rules, logic, and configurations that are applied to client setups. Prior to implementation, the completed checklist is reviewed and formally approved by the client. The approval process is documented and retained, ensuring the customer setup meets the client's specifications and expectations.
1.4 | Upon project completion, the project manager ensures that all deliverables are met, documented, and that the solution is transitioned smoothly to operational teams.
1.3 | For quality control purposes, a secondary review is performed by a senior implementation developer to validate the accuracy of the information configured.
3.1 | Management monitors and tracks the volume of inventory on a daily, weekly, and monthly basis. Reports are generated daily to analyze trends in document receipt and processing. Any significant deviations from expected volume, such as sudden spikes or drops, are flagged for further review to ensure appropriate resource allocation and timely processing.