## Executive Summary
Field | Value
Client | ABC Corporation
Current Phase | TG0 (Design)
Overall Readiness | RED
Next Gate Target | TG0 (Design)
Coverage Score | 42%
Documents Analysed | 4
Documents Parsed | 4
Total Gaps | 7
High-Risk Gaps | 4
TG-1 Initiation | 1%
TG0 Design | 0%
TG1 Implementation | 0%
TG2 Test | 0%
TG3 Deploy/Warranty | 0%
Executive Summary | The ABC Corporation Virtual Mailroom project is currently in the Design (TG0) phase, with significant gaps in foundational documentation. The BRD is an early draft (v0.1) with critical placeholders, and key design documents like the Technical Design Specification and Data Mapping are missing. High-priority risks include the lack of defined client responsibilities and incomplete workflow specifications. To advance, the immediate focus must be on finalizing the BRD, completing core design documents, and defining reporting requirements and SLAs. Without these, proceeding to implementation and testing will be blocked.
— GATE DECISIONS —
TG-1 | CONDITIONAL ¦ Confidence: 45% ¦ Risk: ? ¦ Delay: 2-4 weeks
TG0 | NO-GO ¦ Confidence: 74% ¦ Risk: ? ¦ Delay: 3-6 weeks
TG1 | NO-GO ¦ Confidence: 81% ¦ Risk: ? ¦ Delay: 1-2 months
TG2 | NO-GO ¦ Confidence: 85% ¦ Risk: ? ¦ Delay: 1-2 months
TG3 | NO-GO ¦ Confidence: 100% ¦ Risk: ? ¦ Delay: 1-2 months

## Checklist
Deliverable | Stage Gate | Owner | Status | Confidence | Priority | Est. Effort | Evidence Files | Notes
Business Requirements Document (BRD) | TG-1 (Initiation) | Business Analyst | PARTIAL | HIGH | P1 | Large | ABC Corporation 25080 BRD v0.1.docx | The BRD v0.1 exists but is incomplete, containing placeholders for critical client responsibilities and lacking details on reporting requirements and SLAs. It serves as a foundation but requires significant updates and sign-off.
High-Level Project Plan / Critical Path | TG-1 (Initiation) | PM | PRESENT | HIGH | P1 | Small | ABC Corporation - High-Level Critical Path Project Plan.docx | A detailed project plan outlining phases, timelines, and key activities is provided. It includes estimated durations and highlights overlapping tasks, serving as a clear roadmap for the project.
Client Kickoff / Scope Presentation | TG-1 (Initiation) | PM | MISSING | LOW | P2 | Medium |  | While the project plan implies initiation activities like SOW sign-off and discovery sessions, there is no explicit documentation or mention of a formal client kickoff meeting or scope presentation within the provided documents.
Security & Access Control Documentation | TG-1 (Initiation) | Engineering | PARTIAL | MEDIUM | P2 | Medium | ABC Corporation 25080 BRD v0.1.docx | The BRD mentions SFTP connectivity details including URL, username, port, and SSH key, and IP whitelisting. However, comprehensive security and access control documentation beyond these SFTP specifics is not evident.
Training & Process Awareness Documentation | TG-1 (Initiation) | PM | MISSING | LOW | P1 | Large |  | There is no mention or evidence of training materials or process awareness documentation within the provided files. This is a critical deliverable for client adoption and operational handover.
Workflow / Process Flow Diagram | TG0 (Design) | Engineering | PARTIAL | MEDIUM | P1 | Medium | ABC Corporation -WF Diagram.vsdx | Multiple workflow diagrams are provided, illustrating various aspects of the process. However, the diagrams are explicitly marked as 'illustrative' and not the definitive 'Proposed Solution', indicating they are a starting point but not a final design.
Data Mapping Document | TG0 (Design) | Engineering | MISSING | LOW | P1 | Large |  | No data mapping document is present. While the BRD mentions input/output file specifications and the project plan lists 'Sync-up on Input and Output file specifications', the actual mapping details are missing.
Technical Design Specification | TG0 (Design) | Engineering |  | MEDIUM | P1 | Large | ABC Corporation -WF Diagram.vsdx, ABC Corporation 25080 BRD v0.1.docx | The BRD provides some technical details for SFTP connectivity and client-performed scanning integration. The WF Diagram offers a high-level process flow. However, a comprehensive Technical Design Specification detailing system architecture, integrations, and specific configurations is not present.
BRD Sign-off | TG0 (Design) | Business Analyst / PM | MISSING | LOW | P1 | Small |  | The BRD is version v0.1 and contains placeholders, indicating it is not finalized. There is no evidence of client sign-off on the BRD.
Implementation / Transition Workbook | TG1 (Implementation) | PM / Engineering | MISSING | LOW | P1 | Large |  | No implementation or transition workbook is mentioned or provided. This is a key document for detailing the steps and responsibilities for moving from design to production.
Configuration Documentation | TG1 (Implementation) | Engineering |  | MEDIUM | P1 | Large | ABC Corporation 25080 BRD v0.1.docx | The BRD provides some configuration details for SFTP connectivity and intake folder structures. However, comprehensive configuration documentation for mailroom, workflow, and other system settings is not present.
Reporting Requirements & SLA Documentation | TG1 (Implementation) | PM | MISSING | LOW | P1 | Medium |  | The Project Plan mentions 'Client access, Reporting Requirement and SLA' as a task, but no specific documentation detailing these requirements or SLAs is provided.
Mailroom / Workflow Configuration | TG1 (Implementation) | Engineering |  | MEDIUM | P1 | Large | ABC Corporation -WF Diagram.vsdx, ABC Corporation 25080 BRD v0.1.docx | The WF Diagram provides a high-level overview of the workflow, and the BRD outlines intake channels and SFTP structure. However, detailed configuration specifications for the mailroom and specific workflow rules are not present.
Eligibility & Claims Configuration | TG1 (Implementation) | Engineering |  | MEDIUM | P1 | Large | ABC Corporation 25080 BRD v0.1.docx | The BRD mentions 'Eligibility Matching' in the context of workflow and lists 'Sample Files: One week’s worth of each document type (e.g., claims, EOBs, correspondence)' and 'Eligibility & Provider Files: Current format/layout and sample data' as critical early deliverables. However, specific configuration details for eligibility and claims processing are not provided.
UAT Plan & Test Cases | TG2 (Test) | Engineering / PM |  | MEDIUM | P1 | Large | ABC Corporation - High-Level Critical Path Project Plan.docx | The Project Plan mentions 'Preparing test cases and samples' (10 days) and 'UAT by client' (10 days) within the Testing phase. However, a formal UAT Plan and specific test cases are not provided.
UAT Sign-off / Testing Evidence | TG2 (Test) | Engineering | MISSING | LOW | P1 | Medium |  | As UAT is planned but no plan or test cases exist, there is no evidence of UAT sign-off or testing evidence.
TPM / Compliance Checklist | TG2 (Test) | PM / Engineer | MISSING | LOW | P2 | Medium |  | There is no mention or evidence of a TPM or compliance checklist within the provided documents.
Functional & Volume Testing Evidence | TG2 (Test) | Engineering |  | MEDIUM | P1 | Medium | ABC Corporation - High-Level Critical Path Project Plan.docx | The Project Plan lists 'Functional testing of non-claims' and 'Volume testing' as activities. However, no specific evidence or documentation of these tests having been performed or their results is provided.
M2P / Go-Live Sign-off | TG3 (Deploy/Warranty) | PM / Tech Lead | MISSING | LOW | P1 | Small |  | As the project appears to be in the Design phase with many implementation and testing deliverables missing, there is no evidence of a Go-Live sign-off.
Post-Go-Live Warranty Checklist | TG3 (Deploy/Warranty) | PM | MISSING | LOW | P2 | Small |  | No documentation related to post-go-live warranty or checklists is available.
Lessons Learned Document | TG3 (Deploy/Warranty) | PM | MISSING | LOW | P3 | Small |  | This deliverable is for post-deployment. As the project is in the design phase, no lessons learned document would exist yet.
Final Client Documentation Handoff | TG3 (Deploy/Warranty) | PM | MISSING | LOW | P3 | Medium |  | This is a final deliverable. Given the project's current stage and numerous missing items, this is not yet available.

## Gap Analysis
Gap | Impact | Stage Gate | Recommendation | Responsible Party | Est. Effort | Dependencies
BRD v0.1 contains placeholders for critical client responsibilities regarding pre-scan document preparation and indexing (e.g., document separation, identification, sorting). | HIGH | TG0 (Design) | Schedule a dedicated session with ABC Corporation SMEs to define and document these specific responsibilities within the BRD. Update the BRD with concrete details and obtain client sign-off. | Business Analyst | Medium
Lack of detailed Technical Design Specification, Data Mapping Document, and finalized Workflow/Process Flow Diagram. | HIGH | TG0 (Design) | Engineering team to develop a comprehensive Technical Design Specification, including detailed data mapping and finalize the workflow diagram based on the 'Proposed Solution' referenced in the Visio file. Obtain client review and sign-off. | Engineering | Large | BRD Sign-off
Reporting Requirements & SLA Documentation is missing. | HIGH | TG1 (Implementation) | Schedule a meeting with ABC Corporation to define and document all reporting requirements and Service Level Agreements (SLAs). Create a formal document for client review and sign-off. | PM | Medium | BRD Sign-off
Absence of formal UAT Plan & Test Cases. | HIGH | TG2 (Test) | Develop a comprehensive UAT Plan and detailed test cases based on the finalized requirements and technical design. Engage ABC Corporation for review and approval. | Engineering / PM | Large | Technical Design Specification, BRD Sign-off
No evidence of Training & Process Awareness Documentation. | MEDIUM | TG1 (Implementation) | Develop training materials and process documentation for ABC Corporation end-users and support staff. This should cover system usage, workflows, and support procedures. | PM | Large | Configuration Documentation
Security & Access Control Documentation beyond SFTP specifics is not comprehensive. | MEDIUM | TG1 (Implementation) | Expand on the existing SFTP security details to include broader access control policies, user roles, and data security measures relevant to the SDS platform. | Engineering | Medium
No formal Client Kickoff / Scope Presentation documented. | LOW | TG-1 (Initiation) | Confirm if a client kickoff meeting occurred. If not, schedule one to formally align on scope, project plan, and expectations. Document the meeting outcomes. | PM | Small

## Action Items
# | Action | Owner | Priority | Stage Gate | Deliverable | Est. Effort
1 | Schedule and conduct a session with ABC Corporation SMEs to define and document pre-scan preparation and indexing responsibilities in the BRD. | Business Analyst | P1 | TG0 (Design) | Business Requirements Document (BRD) | Medium
2 | Develop a comprehensive Technical Design Specification, including detailed data mapping and finalize the workflow diagram based on the 'Proposed Solution'. | Engineering | P1 | TG0 (Design) | Technical Design Specification | Large
3 | Define and document Reporting Requirements & SLAs with ABC Corporation. | PM | P1 | TG1 (Implementation) | Reporting Requirements & SLA Documentation | Medium
4 | Develop a formal UAT Plan and detailed test cases. | Engineering / PM | P1 | TG2 (Test) | UAT Plan & Test Cases | Large
5 | Obtain client sign-off on the updated BRD. | Business Analyst / PM | P1 | TG0 (Design) | BRD Sign-off | Small
6 | Develop Training & Process Awareness Documentation. | PM | P1 | TG1 (Implementation) | Training & Process Awareness Documentation | Large
7 | Finalize and document comprehensive Security & Access Control measures. | Engineering | P2 | TG1 (Implementation) | Security & Access Control Documentation | Medium
8 | Confirm occurrence of Client Kickoff / Scope Presentation and document outcomes if not already done. | PM | P2 | TG-1 (Initiation) | Client Kickoff / Scope Presentation | Small
9 | Develop Implementation / Transition Workbook. | PM / Engineering | P1 | TG1 (Implementation) | Implementation / Transition Workbook | Large
10 | Create comprehensive Configuration Documentation. | Engineering | P1 | TG1 (Implementation) | Configuration Documentation | Large
11 | Develop Mailroom / Workflow Configuration details. | Engineering | P1 | TG1 (Implementation) | Mailroom / Workflow Configuration | Large
12 | Develop Eligibility & Claims Configuration details. | Engineering | P1 | TG1 (Implementation) | Eligibility & Claims Configuration | Large
13 | Prepare Functional & Volume Testing Evidence. | Engineering | P1 | TG2 (Test) | Functional & Volume Testing Evidence | Medium

## Gate Decisions
Stage Gate | Decision | Confidence | Risk | Completion | Blockers Met | Blockers Remaining | Optional Gaps | Suggested Delay | Rationale
TG-1 | CONDITIONAL | 45% |  | 40% | 1 | 4 | 1 | 2-4 weeks | Partial readiness at 45%. 4 blocker(s) remain: Business Requirements Document (BRD), Client Kickoff / Scope Presentation, Security & Access Control Documentation. Gate passage is possible once these items are addressed.
TG0 | NO-GO | 74% |  | 12% | 0 | 4 | 0 | 3-6 weeks | Readiness score is 26% — well below the threshold. 3 deliverable(s) are MISSING: Data Mapping Document, Technical Design Specification, BRD Sign-off. Significant work is needed before this gate can be considered.
TG1 | NO-GO | 81% |  | 0% | 0 | 5 | 2 | 1-2 months | Readiness score is 19% — well below the threshold. 5 deliverable(s) are MISSING: Implementation / Transition Workbook, Configuration Documentation, Reporting Requirements & SLA Documentation. Significant work is needed before this gate can be considered.
TG2 | NO-GO | 85% |  | 0% | 0 | 4 | 0 | 1-2 months | Readiness score is 15% — well below the threshold. 4 deliverable(s) are MISSING: UAT Plan & Test Cases, UAT Sign-off / Testing Evidence, TPM / Compliance Checklist. Significant work is needed before this gate can be considered.
TG3 | NO-GO | 100% |  | 0% | 0 | 4 | 0 | 1-2 months | Readiness score is 0% — well below the threshold. 4 deliverable(s) are MISSING: M2P / Go-Live Sign-off, Post-Go-Live Warranty Checklist, Lessons Learned Document. Significant work is needed before this gate can be considered.